## Priority
S/No | Project Name | State | LGA | Town | State | LGA | Town | State | LGA | Town | Date of Award | Category | Nature of Project | Project Target Unit | Performance Level | Project Status | Source of Funding | Project Duration | Duration Unit | Project Cost | Remarks | Contractor
1 | Provision of 2Nos. Motorized Boreholes with Over Head Plastic Tanks | Adamawa | Guyuk | Kola Community | Adamawa | Maiha | Humbutudi Community | Adamawa | Lamurde | Lasun Community |  | Procurement | Capital | 2 Nos |  |  | Budgetary | 8 | Weeks | 18212997.04 |  | Global Legend Integrated Concept Limited
3 | Provision and Installation of 90 Units Solar Street Light | Bauchi | Dass | Dajin | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116832318.75 |  | RKK Inspire Services Limited
2 | Provision of 1 No Mini water Treament Plant in Government Day Secondary School , Yimirlallang | Borno | [9 empty] | Procurement | Capital | 1 No |  |  | Budgetary | 11 | Weeks | 135000000 |  | Visionex Global Concept Cent. Limited
4 | Provision and Installation of 15 Units Solar Street Light | Cross River | Obudu | Uti Jd Agba Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17058562.5 |  | Numora Integrated Services Limited
5 | Construction of 1km Surface Dressed Road | Ekiti | Ado Ekiti | Peace Avenue Road | [7 empty] | Construction | Capital | 1 Km | 100% | Completed | Budgetary | 14 | Weeks | 34405500 |  | Emdiac Solution Limited
6 | Provision and Installation of 15 Units Solar Street Light | Ekiti | Emure | Emure Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17892656.25 |  | Davzino Investments Limited
7 | Construction of 4km Surface Dressed Road with Drainages – Ekiti South Senatorial District | Ekiti |  | Ekiti South Senatorial District | [7 empty] | Construction | Capital | 4 Km | 20% | Ongoing | Budgetary | 8 | Weeks | 194693086.88 |  | Diamond Global Engineering Investment
8 | Provision and Installation of 30 Units Solar Street Light at Dankogi Community | FCT | Abuja Municipal Area Council | Apo Resettlement | [7 empty] | Procurement | Capital | 30 Units | 100% | Completed | Budgetary | 8 | Weeks | 34816867.5 |  | Sidikat Integrataed
9 | Provision and Installation of 15 Units Solar Street Light at Rural Department Headquaters Complex | FCT | Abuja Municipal Area Council | Zone 5 | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 18753656 |  | Tise Agro Services Limited
10 | Provision and Installation of 20 Units Solar Street Light | FCT | Bwari | Fo1 Community | [7 empty] | Procurement | Capital | 20 Units | 100% | Completed | Budgetary | 8 | Weeks | 22601250 |  | All Season Infotech Nigeria Limited
11 | Provision and Installation of 20 Units Solar Street Light | FCT | Kuje | Peggi Community | [7 empty] | Procurement | Capital | 20 Units | 100% | Completed | Budgetary | 8 | Weeks | 23523826.72 |  | Geo-Kooy Environmental Services Limited
12 | Provision and Installation of 90 Units Solar Street Light | Imo | Nwangele | Umuezeala Umuari Communities | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 109325475 |  | Unic & Sons Nigeria Limited
13 | Provision of 2Nos. Motorized Boreholes with Over Head Plastic Tanks at Tise Farm And Marsa Community, Zango Kataf LGA, Kaduna State | Kaduna | Zango Kataf | Tise Farm | Kaduna | Zango Kataf | Marsa Community |  |  |  |  | Procurement | Capital | 2 Nos | 20% | Ongoing | Budgetary | 8 | Weeks | 19206505.8 |  | Altitude Global Links Limited
14 | Provision and Installation of 15 Units Solar Street Light | Kaduna | Kagarko | Deenat Farming Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17865750 |  | Brydoy Engr. Construction Limited
15 | Provision and Installation of 15 Units of Dim Light /Motion Sensors Solar Street Lights | Kaduna | Kagarko | R. B.E. Farming Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 18188625 |  | Afo B. Oil & Gas Limited
16 | Construction of 0.5km Interlocking Road | Kaduna | Kagarko | Tish Farm Community Road | [7 empty] | Construction | Capital | 0.5 Km | 75% | Ongoing | Budgetary | 16 | Weeks | 26273953.13 |  | Leeway System Concerns Limited
17 | Provision and Installation of 15 Units Solar Street Light at Primary Healthcare Kufar Kudu Community | Kano | Gabasawa | Zakirai | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17630000 |  | Ideal Exclusive System & Projects
18 | Provision and Installation of 90 Units Solar Street Light | Kogi | Kabba/Bunu | Ofere Kiri - Oke Ife Community | Kogi | Yagba East | Alu - Igbagun Community |  |  |  |  | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 106193589.5 |  | Zanaghs Global Link Limited
19 | Construction of 1km Interlocking Road Ilorin Road – Sheik Otubu Road | Kwara | Ilorin West | Sheik Otubu Road | [7 empty] | Construction | Capital | 1 Km | 100% | Completed | Budgetary | 6 | Weeks | 62103086 |  | A3 Interbiz Link Services Limited
20 | Provision of 3Nos. Motorized Boreholes with Over Head Plastic Tanks | Lagos | Ojo | Shibiri YS Community | Lagos | Ojo | Iloybo Community |  |  |  |  | Procurement | Capital | 3 Nos | 100% | Completed | Budgetary | 8 | Weeks | 29000520.1 |  | Brydoy Engineering Construction Limited
21 | Provision of 2Nos. Motorized Boreholes with Over Head Plastic Tanks | Lagos | Ojo | Ebun -Balogun Community | Lagos | Ojo | Sibe- Sibe Community |  |  |  |  | Procurement | Capital | 3 Nos | 100% | Completed | Budgetary | 8 | Weeks | 19220275.5 |  | Igaby Lussy Nigeria Limited
22 | Provision of 1No of Solar Powered Borehole With Overhead Plastic Tanks | Lagos | Surulere | Adedoyin Community | [7 empty] | Procurement | Capital | 1 No | 100% | Completed | Budgetary | 8 | Weeks | 8824680 |  | June 6th Global Concept Nigeria Limited
23 | Provision of 2Nos. Motorized Boreholes with Over Head Plastic Tanks | Lagos | Ojo | Ilogbo Elegba | Lagos | Ojo | Agbabiaka Community |  |  |  |  | Procurement | Capital | 2 Nos | 100% | Completed | Budgetary | 8 | Weeks | 21539190 |  | Alzoc Company Nigeria Limited
24 | Provision and Installation of 15 Units Solar Street Light | Lagos | Alimosho | Okonji Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17403750 |  | El-Salam Infotech Nigeria Limited
25 | Provision and Installation of 20 Units Solar Street Light | Lagos | Ojo | Agbabiaka Community | [7 empty] | Procurement | Capital | 20 Units | 100% | Completed | Budgetary | 8 | Weeks | 21794062.5 |  | F&B Construction Limited
26 | Provision and Installation of 20 Units Solar Street Light | Lagos | Agege | Akanbi Adeniran/Olaniyi Community | [7 empty] | Procurement | Capital | 20 Units | 100% | Completed | Budgetary | 8 | Weeks | 22924125 |  | Maiwada Global Concept Limited
27 | Provision and Installation of 20 Units Solar Street Light | Lagos | Alimosho | Femi Daramola Community | [7 empty] | Procurement | Capital | 20 Units | 100% | Completed | Budgetary | 8 | Weeks | 23139375 |  | Laradeb Engineering Consulting Services
28 | Construction of 2.2km Surface Dressed Road – Keana Road | Nasarawa | Keana | Keana Road | [7 empty] | Construction | Capital | 2.2 Km | 100% | Completed | Budgetary | 11 | Weeks | 73999990.31 |  | Yakuba Goni Nigeria Limited
29 | Provision and Installation of 15 Units Solar Street Light | Nasarawa | Karu | Garri Factory Kuchickwo | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17004750 |  | Miralux Concept Nigeria Limited
30 | Construction of 5km Earth Road – Sesati, Gwam Sista Nagopita | Niger | Paikoro | Sesati-Gwam Sista-Nagopita | [7 empty] | Construction | Capital | 5 Km |  |  | Budgetary | 5 | Weeks | 39017418.25 |  | Jabtech Limited
31 | Provision and Installation of 90 Units of Dim Light /Motion Sensors Solar Street Light | Niger | Suleja | Dikko Community | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116735456.25 |  | Acute Options Limited
32 | Provision and Installation of 90 Units Solar Street Light | Niger | Suleja | Zariyawa-Chaza-Kuchiko | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116938867.5 |  | RKK Inspire Services Limited
33 | Provision and Installation of 90 Units Solar Street Light | Niger | Tafa | Karfe, Buntu,Dauto, Yaguru, Kofa, Babon Tunga | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116850615 |  | Ritesim Africa Limited
34 | Provision and Installation of 90 Units Solar Street Light | Niger | Suleja | Maje and kwamba | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116744066.25 |  | Ritesim Africa Limited
35 | Construction of Green House at Yaguru, Dutsen Salanke and Azu-Garam Sabo Wuse Niger State. | Niger | Tafa | Yaguru, Dutsen Salanke and Azu-Garam Sabo Wuse | [7 empty] | Construction | Capital | Construction | 100% | Completed | Budgetary | 11 | Weeks | 51526781.5 |  | Warp Nigeria Limited
36 | Construction of 1km Surface Dressed Road – Monijesu Adigbe Road | Ogun | Obafemi Owode | Monijesu Adigbe Road | [7 empty] | Construction | Capital | 1 km | 100% | Completed | Budgetary | 5 | Weeks | 36401109 |  | Xristom Integrated Limited
37 | Provision and Installation of 15 Units Solar Street Light | Ogun | Ipokia | Agosasa Community | [7 empty] | Procurement | Capital | 15 Units | 100% | Completed | Budgetary | 8 | Weeks | 17538570 |  | Ismade Integrated Nigeria
38 | Provision and Installation of 90 Units Solar Street Light | Ondo | Okitipupa | Okitipupa/Igbokotako | [7 empty] | Procurement | Capital | 90 Units | 100% | Completed | Budgetary | 8 | Weeks | 116832318.75 |  | Kilash Oil Nigeria Limited
39 | Provision of 2Nos. Motorized Boreholes with Over Head Plastic Tanks | Oyo | Ido | Lasokun Community | Oyo | Saki West | Mokola Area, Saki |  |  |  |  | Procurement | Capital | 2 Nos | 100% | Completed | Budgetary | 8 | Weeks | 17997530.72 |  | Seamark Gold Int'l Limited
40 | Provision of 3Nos. Motorized Borehole With Over Head Plastic Tanks | Oyo | Orelope | Okeloko Ogo-Oluwa Community | Oyo | Orelope | Gbedegun Bonni Community | Oyo | Orelope | Oke-Afin Igbo Oba Community |  | Procurement | Capital | 3 Nos | 100% | Completed | Budgetary | 8 | Weeks | 26524216.23 |  | Camp-K Impressions Limited
41 | Provision of 2Nos Solar Powered Borehole With Overhead Plastic Tanks | Oyo | Saki West | Ogungbola Area, Oke-Dio and Arolu Area, Oke Alaafia | [7 empty] | Procurement | Capital | 2 Nos | 100% | Completed | Budgetary | 8 | Weeks | 17231587.2 |  | Swan Medico Limited
42 | Construction of 2km Surface Dressed Road | Oyo | Saki West | Conner Stone Junction Road | [7 empty] | Construction | Capital | 2 Km | 100% | Completed | Budgetary | 16 | Weeks | 72120500 |  | Latokem Nigeria Limited
43 | Construction of 1.5km Surface Dressed Road – Ekereborikiri, Epelema, Rivers State | Rivers | Port Harcourt | Ekereborikiri | [7 empty] | Construction | Capital | 1.5 Km |  |  | Budgetary | 6 | Weeks | 59000563.13 |  | Xristom Integrated Tech. Limited
44 | Provision of 2Nos Solar Powered Borehole With Overhead Plastic Tanks | Sokoto | Wamako | Arkilla Magaji Community | Sokoto | Wamako | Marmaro, Gidan Shema Community |  |  |  |  | Procurement | Capital | 2 Nos |  |  | Budgetary | 8 | Weeks | 18231900 |  | IC Edros Limited
45
46
47
48
49
50
51